## Gantt Chart w % Complete
#NAME?
GANTT CHART TEMPLATE |  |  |  | Build better gantt charts with TeamGantt for FREE!
To edit this chart, you must first make a copy. Go to File, the select Make a Copy.
* = an automatically calculated cell
| TASK NAME | START DATE | DAY OF MONTH* | END DATE | DURATION* (WORK DAYS) | DAYS COMPLETE* | DAYS REMAINING* | TEAM MEMBER | PERCENT COMPLETE | WEEK 1 | WEEK 2 | WEEK 3 | WEEK 4
First Sample Project
| Write Landing Page Copy | 2018-01-05 | 5 | 2018-01-08 | 3 | 3 | 0 | Nathan | 100%
| Approve Page Copy | 2018-01-08 | 8 | 2018-01-11 | 3 | 2.4 | 0.6 | Meredith | 80%
| Review Landing Page Design | 2018-01-11 | 11 | 2018-01-16 | 5 | 3 | 2 | Brandon | 60%
| Build Landing Page | 2018-01-14 | 14 | 2018-01-19 | 5 | 2 | 3 | Michael | 40%
| Code Review Landing Page | 2018-01-17 | 17 | 2018-01-23 | 6 | 1.2 | 4.8 | Rachel | 20%
Second Sample Project
| Write Promotional Email | 2018-01-09 | 9 | 2018-01-12 | 3 | 3 | 0 | Nathan | 100%
| Design Promotional Email | 2018-01-12 | 12 | 2018-01-19 | 7 | 5.6 | 1.4 | Meredith | 80%
| Send Promotional Email | 2018-01-17 | 17 | 2018-01-19 | 2 | 1.2 | 0.8 | Brandon | 60%
| Analyze Campaign Results | 2018-01-22 | 22 | 2018-01-26 | 4 | 1.6 | 2.4 | Michael | 40%
Third Sample Project
| Plan Agenda for Meeting | 2018-01-15 | 15 | 2018-01-19 | 4 | 4 | 0 | Nathan | 100%
| Reserve Room | 2018-01-22 | 22 | 2018-01-23 | 1 | 0.8 | 0.2 | Meredith | 80%
| Finalize Presentation | 2018-01-22 | 22 | 2018-01-26 | 4 | 2.4 | 1.6 | Brandon | 60%
| Approve Presentation | 2018-01-26 | 26 | 2018-01-29 | 3 | 1.2 | 1.8 | Michael | 40%
| Create Invitations | 2018-01-22 | 22 | 2018-01-25 | 3 | 0.6 | 2.4 | Rachel | 20%
Fourth Sample Project
| Rewrite Online Calculator | 2018-01-15 | 15 | 2018-01-24 | 9 | 9 | 0 | Nathan | 100%
| Code Review Calculator | 2018-01-25 | 25 | 2018-01-30 | 5 | 4 | 1 | Meredith | 80%
| Update Messaging | 2018-01-24 | 24 | 2018-01-30 | 6 | 3.6 | 2.4 | Michael | 60%
| Publish Calculator | 2018-01-30 | 30 | 2018-01-31 | 1 | 0 | 1 | Rachel | 0%

## Basic Gantt Chart
GANTT CHART TEMPLATE
* = an automatically calculated cell
| TASK NAME | START DATE | END DATE | START ON DAY* | DURATION* (WORK DAYS) | PERCENT COMPLETE | WEEK 1 | WEEK 2 | WEEK 3 | WEEK 4
First Sample Project
| Literature studies | 2018-11-05 | 2018-11-09 | 0 | 4 | 100%
| Setup of the ** | 2018-11-07 | 2018-11-14 | 2 | 7 | 100%
| Design a filter for the fluorescence measurement | 2018-11-07 | 2018-11-11 | 2 | 4 | 100%
| Create a nonlinear mapping | 2018-11-08 | 2018-11-12 | 3 | 4 | 100%
| Estimate the phase shift of the fluorescence measurement |  |  | -43409 |  | 100%
| Create a transfer function |  |  | -43409 |  | 100%
| Create a feedback controller w.r.t |  |  | -43409 |  | 100%
| Analyze the robustness |  |  | -43409 |  | 100%
| Test the system on the plants |  |  | -43409 |  | 100%
| Write project report | 2018-12-05 | 2018-12-19 | 30 | 14

## Manual Chart
TASK NAME | START DATE | END DATE | STUDY WEEK 1 |  |  |  |  | STUDY WEEK 2 |  |  |  |  | STUDY WEEK 3 |  |  |  |  | STUDY WEEK 4 |  |  |  |  | STUDY WEEK 5 |  |  |  |  | STUDY WEEK 6 |  |  |  |  | STUDY WEEK 7 |  |  |  |  | BREAK |  | STUDY WEEK 8 |  |  |  |  | ----
|  |  | M | T | W | Th | F | M | T | W | Th | F | M | T | W | Th | F | M | T | W | Th | F | M | T | W | Th | F | M | T | W | Th | F | M | T | W | Th | F |  |  | M | T | W | Th | F | M | T | W | Th | F
|  |  | 2018-11-05 | 2018-11-06 | 2018-11-07 | 2018-11-08 | 2018-11-09 | 2018-11-12 | 2018-11-13 | 2018-11-14 | 2018-11-15 | 2018-11-16 | 2018-11-19 | 2018-11-20 | 2018-11-21 | 2018-11-22 | 2018-11-23 | 2018-11-26 | 2018-11-27 | 2018-11-28 | 2018-11-29 | 2018-11-30 | 2018-12-03 | 2018-12-04 | 2018-12-05 | 2018-12-06 | 2018-12-07 | 2018-12-10 | 2018-12-11 | 2018-12-12 | 2018-12-13 | 2018-12-14 | 2018-12-17 | 2018-12-18 | 2018-12-19 | 2018-12-20 | 2018-12-21 | 2018-12-24 | 2018-01-13 | 2018-01-14 | 2018-01-15 | 2018-01-16 | 2018-01-17 | 2018-01-18 | 2018-01-21 | 2019-01-01 | 2019-01-02 | 2019-01-03 | 2019-01-04
Literature studies | 2018-11-05 | 2018-11-13 | bar: STUDY WEEK 1 M to STUDY WEEK 2 T
Design a filter for the fluorescence measurement | 2018-11-07 | 2018-11-13 | bar: STUDY WEEK 1 W to STUDY WEEK 2 T
Setup of the system (computer/components/etc) | 2018-11-07 | 2018-11-13 | bar: STUDY WEEK 1 W to STUDY WEEK 2 T
Create a nonlinear mapping | 2018-11-08 | 2018-11-14 | bar: STUDY WEEK 1 Th to STUDY WEEK 2 W
Estimate the phase shift of the fluorescence measurement | 2018-11-15 | 2018-11-23 | bar: STUDY WEEK 2 M to STUDY WEEK 2 T; STUDY WEEK 2 Th to STUDY WEEK 3 F
Create a transfer function | 2018-11-23 | 2018-11-30 | bar: STUDY WEEK 2 M to STUDY WEEK 2 T; STUDY WEEK 3 F to STUDY WEEK 4 F
Create a feedback controller w.r.t | 2018-11-30 | 2018-12-06 | bar: STUDY WEEK 2 M to STUDY WEEK 2 T; STUDY WEEK 4 F to STUDY WEEK 5 F
Analyze the robustness | 2018-12-06 | 2018-12-11 | bar: STUDY WEEK 2 M to STUDY WEEK 2 T; STUDY WEEK 5 Th to STUDY WEEK 6 T
Test the system on the plants | 2018-12-11 | 2018-12-14 | bar: STUDY WEEK 2 M to STUDY WEEK 2 T; STUDY WEEK 6 T to STUDY WEEK 6 F
Write project draft report | 2018-12-05 | 2018-12-19 | bar: STUDY WEEK 2 M to STUDY WEEK 2 T; STUDY WEEK 5 W to STUDY WEEK 7 W
Write paper review | 2018-12-19 | 2018-12-21 | bar: STUDY WEEK 2 M to STUDY WEEK 2 T; STUDY WEEK 7 W to STUDY WEEK 7 F
Write final paper | 2019-01-14 | 2019-01-18 | bar: STUDY WEEK 2 M to STUDY WEEK 2 T
Prepare demostration | 2019-01-17 | 2019-01-21 | bar: STUDY WEEK 2 M to STUDY WEEK 2 T